## TMS-YC
DATE | WORK DETAILS | TIME FRAME | COMMENTS
05-Mar-2026 | Pre-development phase — requirements gathering, planning & design. No commit history exists for this period. | 5 Mar – 24 May 2026 | Git repository history begins 25-May-2026; add specifics here if needed for the record.
25-May-2026 | Initial commit of the Yahweh Care Ticket Management System. Set up Vercel serverless deployment for the backend (TypeScript build/config fixes); configured CI/CD workflow (GitHub Actions) replacing the earlier Azure deploy path; fixed duplicate-import and build-path errors; pointed the frontend at the production backend URL. | 25 – 26 May 2026 | Application deployed and reachable on Vercel for the first time.
27-May-2026 | UI branding v1 — glow effects across buttons/cards/badges/nav; corporate colour palette (violet badges, brand breadcrumb); Calendar page redesign (hero header, circle dates, priority-dot pills); fixed a blank-screen crash and a React hook-order error; corrected Staff Performance SLA/avgHours/rating calculations. | 27 – 28 May 2026 | First visual identity pass; resolved a blocking blank-screen bug.
29-May-2026 | Added the Analytics dashboard (admin-only). Multiple theme iterations (dark glossy-black + green accents, then PowerApps-style navy/white). Enterprise sidebar redesign with toggle and profile dropdown; PDF export. Wired Staff CRUD, tickets/lookups/notifications and the Scheduled Reports module to the real database; full DB↔application schema audit; domain-restricted login. | 29 – 30 May 2026 | Core data (staff, tickets, reports) now backed by the live database instead of mock data.
31-May-2026 | Built the organisational hierarchy — departments, positions, Org Chart page with row-level security; DB migration for org hierarchy; bootstrap-admin protection (cannot be demoted or deactivated); Org Chart visual redesign matching the company's chart, connector-line fixes. | 31 May 2026 | Org Chart feature completed end-to-end in a single day.
03-Jun-2026 | Rebuilt as a full multi-page application with hash-based routing. Create Ticket form wired to real lookup data; critical-path ticket approval workflow; ticket escalation; Australian public-holiday calendar with state filter; full Analytics BI page; recursive Org Chart component; Staff Management CRUD groundwork for Microsoft Entra login. | 3 – 4 Jun 2026 | Major structural rebuild — app went from a single mock page to a full routed application.
05-Jun-2026 | Aligned Org Chart/Staff API with the actual DB schema. Implemented Microsoft Entra (MSAL) login, replaced with a zero-dependency PKCE OAuth flow after CDN issues; added an email/password fallback login; sign-out flow; session/auth hardening (stateless JWT-in-state to survive Vercel's serverless model); real logged-in user shown in sidebar. | 5 – 6 Jun 2026 | Authentication went through several iterations before landing on a stable, serverless-compatible design.
07-Jun-2026 | Wired the Tickets page and Create Ticket to the real API; rewrote Staff Performance page with live metrics/insights; role-based ticket visibility and data scoping (admin/director/manager/staff/approver); Calendar redesign with insights and a week view; full Tickets page redesign (table, filters, drawer); new TopBar; Scheduled Reports rewritten (15 report types, Excel/CSV export, email); full dark mode implementation. | 7 Jun 2026 | Single-day, high-output phase covering most of the reporting and ticketing UI.
08-Jun-2026 | Added the push notification system; full responsive layout (mobile/tablet/desktop); premium dark/light mode design sweep across every page; integrated Resend for ticket-event and report emails; corrected the SLA-compliance formula; multiple SQL/schema alignment fixes for tickets and reports; brief security/performance hardening pass (reverted same day after causing regressions); self-assign fix for Create Ticket. | 8 Jun 2026 | Security/auth hardening attempted but rolled back same day — flagged for a safer retry later.
09-Jun-2026 | Bootstrap-admin protections; full ticket workflow — assignee tab, extension requests, approver-gated actions, admin-only delete; file attachments and work notes on tickets; per-user “Pending My Approval” tab; push notification VAPID/Uint8Array fixes; real email sending for scheduled reports via Resend with an Excel attachment. | 9 – 10 Jun 2026 | Ticket lifecycle (create → assign → approve → resolve) fully wired for the first time.
11-Jun-2026 | Built the Ticket Log page (full lifecycle timeline for managers/directors/admin); introduced automated unit testing (Jest) — grew from 67 to 210 passing tests across 15 suites the same day; close-ticket workflow (requester confirms resolution); “Ready to Close” renamed to “Pending Closure”; auth token auto-refresh (authFetch) rolled out across the app; performance pass removing runtime Babel transpilation. | 11 Jun 2026 | First introduction of automated regression testing — a turning point for release safety.
12-Jun-2026 | Push notification VAPID setup and error-logging fixes; build pipeline minification (Terser, 522KB→333KB); Resend email service integration; priority/assignee/date-range filters on Tickets and Ticket Log; cron jobs for email retry, approval reminders and daily summaries; notification bell with pagination; stabilised the full unit test suite to 106/106 passing. | 12 – 13 Jun 2026 | Build and notification infrastructure hardened; test suite fully green.
14-Jun-2026 | Role-aware email templates; category icon-picker redesign for Create Ticket; replaced every emoji/glyph across the entire application with a proper SVG icon system (Tickets, Calendar, Analytics, Org Chart, Reports, Staff Management, login, ticket drawer); rebuilt web push notifications through several iterations (added, removed, re-added) before settling on a stable implementation with a branded logout page; added 41 unit tests covering push/email/notification-click behaviour. | 14 – 15 Jun 2026 | Visual polish (icons) and push notifications both reached their stable, final form this phase.
22-Jun-2026 | Performance optimisation pass — memoised Dashboard/Tickets/Analytics computations, debounced search, paginated the ticket list, added a global ticket cache (fetch once, seed every page), service-worker app-shell caching; advanced Calendar with Month/Week/Day/Agenda views and drag-and-drop; evaluated an Azure deployment path (workflows, static web app config) as an alternative to Vercel. | 22 – 24 Jun 2026 | Focus shifted from features to load-time and responsiveness.
30-Jun-2026 | Fixed assignee notifications on ticket create/reassign; repository restructure; CI/CD pipeline fixes (Node version alignment, Azure Static Web Apps auth workaround, new staging workflows targeting Vercel + Neon). | 30 Jun – 2 Jul 2026 | Groundwork laid for the eventual move to a Vercel-only deployment (see next phase).
03-Jul-2026 | Repaired database migrations (001–008) and hardened auth queries; added wmxsolutions.com.au to the allowed login domains; pointed the frontend at the live Vercel backend (was still targeting a dead Azure host); fixed an Org Chart 500 error from missing profile columns and corrected the chart data to match the authoritative org chart; excluded the “No Department” bucket from Team Comparison; fixed a bug that emailed users about their own ticket comments; made Calendar drag-to-reschedule actually persist; professional Org Chart redesign (avatars, zoom, search). | 3 Jul 2026 | Recovered from a database/domain misconfiguration that had been silently breaking logins and the org chart for some staff.
04-Jul-2026 | Bootstrap-admin-only delete permissions for staff/positions; fixed SLA Compliance showing 0% and Pending Approval tickets missing their Approve button; built a real My Profile/Settings page; replaced the placeholder logo with the real Yahweh Care brand logo; authored DEVELOPER_HANDOVER.md (Version 1); renamed project folders to their current names (YCTMFrontend/YCTMBackend); built the full staff-deactivation lifecycle (Ex-Staff page, Activity Log with export/archive/delete plus a regression test); professional redesign of Staff Management (badges, muted corporate palette) and an app-wide rebrand to Yahweh Care's purple brand colour. | 4 Jul 2026 | Largest single day of the project — documentation, rebrand and staff-lifecycle features all landed together.
05-Jul-2026 | Extended the brand-colour rollout to Org Chart, Staff Management position badges and Scheduled Reports; fixed a stray-circle rendering bug on Org Chart cards; refined avatar/badge colour tones (Bootstrap Admin gold, Finance green, Employment/login badges); removed the unused legacy frontend-example/ folder. | 5 Jul 2026 | Rebrand completed and visually consistent across every page.
05-Jul-2026 | Project went live in production, including Azure migration (per your note). | 5 Jul 2026 | Flagged for your review: this conflicts with what I can verify directly — the live production app I've tested this session runs on Vercel (yahweahcare-tkt-mgmt.vercel.app / yahweahcare-tkt-mgmt-hx48.vercel.app), and DEVELOPER_HANDOVER.md documents both Azure GitHub Actions workflows as dead/disabled (target Azure resources no longer exist). Please double-check and correct this row if the Azure details differ from what's recorded here.

## TMS-YPC
DATE | WORK DETAILS | TIME FRAME | COMMENTS

## HRMS-YAHWEH
DATE | WORK DETAILS | TIME FRAME | COMMENTS